## Hour Log
Subject | Amount of hours | Date | Description
Project setup & architecture | 2 | 2025-12-17 | Initialized Vue 3 project using Vite. Set up folder structure, Vue Router, Pinia state management and basic configuration following DTT standards.
Style guide implementation | 3 | 2025-12-17 | Translated DTT style guide into CSS variables. Implemented global colors, typography, base styles and ensured consistency across components.
Navigation header | 2 | 2025-12-18 | Implemented fixed navigation header with active route indication and responsive behavior using Vue Router.
API service setup | 2.5 | 2025-12-18 | Created reusable API service for house endpoints including authorization header handling and error management.
House overview page | 5 | 2025-12-18 | Implemented homepage with house listings. Created reusable HouseCard component and connected data via Pinia store.
Search & sorting | 3.5 | 2025-12-19 | Implemented client-side search with clear functionality, result indication and sorting by price.
House detail page | 3 | 2025-12-19 | Built detailed house view displaying all listing information with conditional edit and delete actions.
Create listing form | 2 | 2025-12-20 | Implemented reusable form component for creating listings with validation, error handling and redirect after submission.
Edit listing functionality | 2 | 2025-12-20 | Extended form component to support editing listings with pre-filled data and validation.
Delete listing | 1.5 | 2025-12-20 | Implemented delete functionality with confirmation dialog and API integration.
Responsive adjustments | 2 | 2025-12-21 | Adjusted layout and typography for mobile and tablet breakpoints according to design specifications.
Code cleanup & documentation | 1.5 | 2025-12-21 | Refactored components, improved naming consistency and added comments for clarity and maintainability.
Total amount |  | 30-31h